Nameless Retail Company

BI Justification

Retail Store Communication Failure Analysis and Prediction System

Date: June 2026

Author(s): Lane Dorscher

Sponsor(s): Bellevue University, DSC-300

Table of Contents

Executive Summary	4

Business Opportunities	5

Business Objectives	5

Business Initiatives	5

Business Processes	5

Project description	6

Project Goals	6

Key Deliverables	6

Project Timeline	6

Proposed Approach	6

Alternative Approaches	6

Project Scope	7

Project Out-of-Scope	7

Project Financials	8

Project Budget	8

Total Cost of Ownership (TCO)	8

ROI	9

Dependancies, assumptions, Risks and issues	10

Project Dependencies	10

Project Assumptions	10

Project Risks	10

Project Issues	11

Business sponsors and stakeholders	12

Business Sponsors	12

Project Stakeholders	12

Approvals	13

Appendix: Background Materials	14

Authors and contributors	14

# Executive Summary

|  | Write this after completing the remainder of business justification document. The executive summary is the justification’s abstract and needs to convey its key elements. This section creates the first impression for many stakeholders and often establishes their overall project expectations. |
| --- | --- |

|  | The executive summary should include a brief summary of the following: - Business Opportunities - Key Deliverables - Critical Success Factors (CSF) - Key Project Metrics: Milestones, Costs, Resources, ROI |
| --- | --- |

# Business Opportunities

Retail stores rely on stable network connections to transmit critical sales, inventory, financial, and operational data to corporate systems. Communication failures can delay reporting, disrupt store operations, and require manual intervention from Information Technology teams. While incidents are currently addressed after they occur, the organization has limited visibility into the recurring causes and patterns behind these disruptions.

This project will leverage business intelligence, predictive analytics, and machine learning to analyze historical communication failures, identify recurring trends and root causes, and predict future incidents. By providing actionable insights into store connectivity issues, the organization can make informed decisions regarding infrastructure improvements, hardware replacement, ISP performance, and network reliability while reducing downtime and operational disruptions.

## Business Objectives

- Identify recurring causes of store communication failures.

- Improve the success rate of nightly data transmissions.

- Reduce store communication-related incidents.

- Reduce IT incident response workload.

- Improve store-to-corporate system availability.

- Support data-driven infrastructure decisions.

- Metrics:

  - Communication failure rate

  - Data transmission success rate

  - Mean Time to Resolve (MTTR)

  - Number of outages per month

  - Prediction accuracy

  - Incident recurrence rate

  - Outage duration by store and ISP

## Business Initiatives

- Improve retail operational reliability.

- Increase business continuity through proactive monitoring.

- Support data-driven IT decision-making.

- Reduce downtime through predictive incident detection.

- Improve visibility into communication failure trends and root causes.

- Deliverables:

  - Communication failure analytics platform

  - Machine learning prediction model

  - Risk dashboards

  - Automated alerts

  - Incident trend and root cause reporting

## Business Processes

- Store Data Transmission

  - Supports the transfer of sales, inventory, and financial data from stores to corporate systems.

  - Current Bottleneck: Failures are often detected only after transmissions have been interrupted, resulting in delayed corrective action.

- Incident Management

  - Supports IT teams responsible for investigating and resolving store communication issues.

  - Current Bottleneck: Historical incident information is not centrally analyzed to identify recurring patterns and root causes.

- Business Reporting

  - Supports corporate reporting and analytics that depend on timely store data.

  - Current Bottleneck: Failed or delayed transmissions can impact reporting accuracy and availability.

- Infrastructure Planning

  - Supports decisions regarding ISP providers, network equipment, and communication infrastructure.

  - Current Bottleneck: Decisions are often based on individual incidents rather than long-term trend analysis.

# Project description

The Retail Store Communication Failure Analysis and Prediction System is a business intelligence and data science solution designed to analyze historical communication failures and predict future disruptions between retail stores and corporate systems. The system will combine network performance data, transmission activity, ISP information, and incident records to identify trends, recurring failure patterns, and risk factors associated with store communication outages. These insights will support proactive maintenance, infrastructure planning, and operational decision-making while reducing downtime and improving the reliability of critical business systems.

## Project Goals

- Analyze historical communication failures and outage trends.

- Identify recurring causes of communication disruptions.

- Predict future store communication failures.

- Improve the success rate of nightly data transmissions.

- Reduce downtime and operational disruptions.

- Support proactive incident management.

- Improve visibility into network performance and infrastructure reliability.

## Key Deliverables

- Business Applications and Processes

  - Communication reliability dashboard

  - Automated risk alerting system

  - Infrastructure performance reporting

- Analytical Capabilities

  - Communication failure trend analysis

  - Root cause analysis

  - Machine learning prediction model

  - Risk scoring and forecasting

- Data Sources

  - Network performance metrics

  - Incident management records

  - Store transmission logs

  - ISP connectivity data

  - Historical outage records

- Data Integration and Cleansing

  - Consolidation of data from multiple sources

  - Data validation and cleansing processes

  - Standardized incident and transmission records

## Project Timeline

| Milestone | Target Date |
| --- | --- |
| Requirements Gathering and Business Analysis | Week 1-2 |
| Data Collection and Data Quality Assessment | Week 3-4 |
| Trend Analysis and Root Cause Investigation | Week 5-6 |
| Predictive Model Development | Week 7-8 |
| Dashboard and Reporting Development | Week 9 |
| Testing, Validation, and Final Recommendations | Week 10 |

## Proposed Approach

Historical network performance data, transmission activity, ISP information, and incident records will be collected from existing monitoring and support systems. The data will be cleansed, standardized, and integrated into a centralized repository for analysis. Business intelligence reporting and analytical techniques will be used to identify trends, recurring failure patterns, and infrastructure performance issues. Machine learning models will then be developed to predict future communication failures and generate risk scores for affected stores. Results will be delivered through dashboards, reports, and automated alerts that support proactive decision-making by IT Operations and Network Infrastructure teams.

## Alternative Approaches

## Alternative approaches considered include continuing with traditional threshold-based monitoring, expanding network redundancy solutions, and relying solely on incident reporting systems. While these approaches help detect and respond to outages, they provide limited visibility into recurring causes and future risk. The proposed solution combines historical analysis and predictive analytics to support both operational awareness and proactive infrastructure planning.

## Project Scope

The scope of this project is to design and implement a business intelligence and data science solution that analyzes historical store communication failures and predicts future communication disruptions. The project includes the collection and analysis of network performance metrics, transmission logs, ISP connectivity data, and incident records to identify recurring outage patterns, root causes, and risk factors. Deliverables include analytical dashboards, trend reporting, root cause analysis, predictive models, and automated alerts that support IT Operations and Network Infrastructure teams in making informed decisions regarding network reliability, hardware replacement, and ISP performance.

## Project Out-of-Scope

This project will not replace existing network monitoring, incident management, or communication systems. The project does not include network hardware upgrades, ISP replacement projects, infrastructure redesign, or the implementation of new failover technologies. Automated remediation and outage resolution capabilities are also outside the scope of this project. The solution is limited to analyzing historical communication failures, identifying trends and root causes, generating predictive insights, and providing reporting and alerting capabilities to support decision-making.

# Project Financials

The Retail Store Communication Failure Analysis and Prediction System will require investment in software development, data integration, analytics infrastructure, and employee training. While the project introduces upfront implementation costs, it is expected to reduce operational expenses associated with recurring communication failures, reactive IT support, and extended store downtime. The project is expected to provide long-term value through improved infrastructure planning, increase network reliability, and more efficient use of IT resources.

## Project Budget

| Category | Estimated Cost |
| --- | --- |
| Internal Development Labor | $180,000 |
| Data Engineering & Integration | $60,000 |
| Machine Learning Development | $70,000 |
| BI Dashboard Development | $35,000 |
| Testing & Validation | $25,000 |
| Training & Documentation | $15,000 |
| Contingency (10%) | $38,500 |
| Estimated Project Cost | $423,500 |

## Total Cost of Ownership (TCO)

Annual operational costs will include system maintenance, model retraining, software licensing, cloud infrasture, and ongoing support.

| Annual Category | Estimated Cost |
| --- | --- |
| Infrastructure / Cloud | $20,000 |
| Software Licensing | $10,000 |
| Model Maintenance | $15,000 |
| Application Support | $10,000 |
| Continuous Improvements | $15,000 |
| Annual TCO | $90,000 |

## ROI

The Retail Store Communication Failure Analysis and Prediction System is expected to provide financial value by reducing store communication failures and minimizing the business impact of extended outages. Communication disruptions can delay nightly sales, inventory, and financial data transmissions, requiring manual intervention by IT personnel and delaying business reporting. By identifying recurring causes of failures and predicting future communication issues, the organization can proactively address infrastructure problems before they result in prolonged outages.

The solution is expected to reduce IT troubleshooting time, improve successful nightly data transmissions, and help prioritize hardware replacement and ISP improvements using data rather than reactive decision-making. Preventing recurring outages can reduce overtime costs, improve employee productivity, minimize reporting delays, and reduce unnecessary infrastructure expenditures.

Based on an estimated 20–30% reduction in recurring communication incidents, the project is expected to:

- Reduce annual IT support labor costs associated with communication outages.

- Reduce operational disruptions caused by failed nightly data transmissions.

- Improve infrastructure investment decisions by identifying stores with recurring hardware or ISP issues.

- Reduce unnecessary hardware replacement through data-driven analysis.

- Improve the availability of business-critical operational data.

The project is expected to recover its implementation costs within two to three years through reduced operational costs, improved IT efficiency, and avoided revenue impacts associated with prolonged store communication failures.

# Dependancies, assumptions, Risks and issues

## Project Dependencies

| Dependency | Impact |
| --- | --- |
| Historical incident records | Required for trend analysis and model training |
| Network monitoring data | Required for communication reliability analysis. |
| Store transmission logs | Required for identifying transmission-related failures. |
| Subject matter experts | Required to validate business processes and analytical results. |
| Executive approval and funding | Required before project initiation. |

## Project Assumptions

| Assumption | Impact |
| --- | --- |
| Historical incident data is accurate. | Reliable models can be developed. |
| Monitoring systems capture sufficient network metrics. | Predictive analysis is possible. |
| Data from multiple systems can be integrated. | A complete analytical view can be created. |
| Business users will validate analytical results. | Models can be refined using operational feedback. |
| Communication data will continue to be collected. | Models can be retrained over time. |

## Project Risks

| Risk | Mitigation |
| --- | --- |
| Poor data quality | Perform data profiling, cleansing, and validation before model development |
| Insufficient historical data | Expand data collection or extend the analysis period. |
| Low prediction accuracy | Continuous retrain and validate models with new data |
| Changing network infrastructure | Update analytical models as infrasctructure changes occur |
| Limited user adoption | Provide dashboards, training, and involve users throughout development |

## Project Issues

| Issue | Description |
| --- | --- |
| Incomplete incident documentation | Some historical incidents may not have confirmed root cause |
| Multiple monitoring systems | Data may have different formats and require additional transformation before analysis |
| Missing infrastructure history | Hardware replacement records may be incomplete |
| External ISP outages | Some failures may have limited diagnostic information available |

# Business sponsors and stakeholders

## Business Sponsors

| Title | Organization Group | Project Role |
| --- | --- | --- |
| Chief Information Officer (CIO) | Executive Leadership | Executive Sponsor |
| Director of Information Technology | IT Operations | Business Sponsor |
| Director of Network Infrastructure | Infrastructure | Business Sponsor |

## Project Stakeholders

| Title | Organization Group | Project Role |
| --- | --- | --- |
| IT Operations Manager | IT Operations | Primary User |
| Network Infrastructure Manager | Infrastructure | Primary User |
| Systems Administrator | IT Operations | Subject Matter Expert |
| Network Engineer | Infrastructure | Subject Matter Expert |
| Business Intelligence Analyst | Business Intelligence | Report Customer |
| Store Operations Manager | Store Operations | Business Stakeholder |
| Service Desk Manager | IT Support | Information Consumer |

# Approvals

|  | It is a best practice to obtain sign-off approval of each project milestone. An organization’s policies and culture will dictate who the approvers will be, but typically the sponsors and key stakeholders are included. |
| --- | --- |

| Title | Name | Approval Date |
| --- | --- | --- |

# Appendix: Background Materials

|  | This section includes all background or supporting materials for the BI Justification. These materials may include more detailed analysis of the following: - Project plan - Project Budget - ROI Calculation |
| --- | --- |

## Authors and contributors

|  | List all the people involved in obtaining and analyzing the requirements along with the authors of this deliverable. |
| --- | --- |